## Sheet1
Group | Resources | Tasks | ETA(in hrs) | Status | Review Comment
| Terraform AWS EKS | Used AWS Terraform AWS EKS module registry https://github.com/terraform-aws-modules/terraform-aws-eks
Security | IAM | Identify and Create an AWS EKS Service Role | 0.5 | Completed
|  | Create an IAM role and policy for worker nodes | 0.5
|  | Add the CloudWatchLogs policy also to the worker node |  | Completed
Networking | VPC | Use the same VPC created for ECS cluster Create 3 private subnets with following CIDR 10.11.128.0/19 - private A 10.11.160.0/19 - private B 10.11.192.0/19 - private C | 3
Completed
| Security Group | Identify and Create new security group for VPC | 1 | Completed
|  | Decide the ingress for the security group created for VPC | 1 | Completed
|  | Create security group for worker nodes | 1 | Completed
|  | Decide the ingress for the security group created for worker node | 1 | Completed
Compute | EKS | Create an EKS Cluster | 1 | Completed
| Auto Scaling Group | Create Launch Configuration and Auto Scaling Group | 2 | Completed
|  | Decide the AMI to be used | 1 | Completed
|  | Use the same instance as being used in ECS | 1 | Completed
|  | Identify the desired, maximum and minimum number of nodes 3 - 3 zones | 1 | Completed
Management | CloudTrail | Configure Cloud Trail for EKS | 3
Other Tools
Other Tools | kubectl | Install and Configure kubectl for Amazon EKS | 0 | Completed | API Server endpoint is it a public or private? How do we secure it? API server endpoint certificate authentication with Okta.
| aws-iam-authenticator | Install and configure aws-iam-authenticator for Amazon EKS | 0 | Completed
|  | Install and Configure Okta to authenticate kubectl and Helm | 0 | Completed
|  | Test your configuration kubectl get svc | 0 | Completed
|  | Enable worker nodes to join EKS cluster Currently it's a manual steps it needs to automated. | 4 | Completed
| Helm | Install and Configure Helm using Terraform | 3 | Completed
|  | Install Istio along with Grafana, Jaeger and Service Graph using Helm | 3 | Completed
|  | Configure Grafana |  | Incomplete | Public or Private?
|  | Verify the Services and Pods in Istio System | 1 | Completed
| Logging | Configure the incubator/fluentd-cloudwatch | 2 | Completed | This project needs to be checked in artefacts because it's github project and we have made some changes to make it work.
|  | Install incubator/fluentd-cloudwatch using Helm | 2 | Completed
|  | Configure the Lambda function to send the logs to logentries | 3 | Completed
Microservices Deployment
Common Prep Steps
| Gateway | Create a gateway for the EKS cluster | 2 | Completed | Write all the kubernetes yamls using terraform
|  | Identify whether to use Istio default controller or AWS ALB ingress controller project | 3 | Completed
| Mutual TLS | Decide whether mutual TLS needs to be used for services |  |  | Find out more in detail about MTLS and RBAC
Configure MeshPolicy for Istio Service Mesh
| RBAC | Decide whether RBAC needs to be used for services or not
Enable RBAC config
Update the pod also to enable this feature
staging-avenger-server
| Pod | Create pod for staging-avenger-server | 2 | Completed
|  | Identify the number of replicas to run |  | Completed | Same as staging and prod
|  | Specify the avenger-server image to be used for container |  | Completed
|  | Specify the port mappings for container |  | Completed
|  | Identify the environment vairables to be used and can be moved to ConfigMaps | 3 | Completed
|  | Identify if some variable can be moved as Secrets | 2 | Completed
|  | Configure the container for health checks | 2 | Completed
| Service | Create the service for staging-avenger-server pod | 2 | Completed
| Virtual Service | Create Virtual Service for staging-avenger-server service | 4 | Completed
|  | Identify the host to be used |  | Completed
|  | Identify if any request routing rules needs to be applied |  | Completed
|  | Specify if timeout and retries needs to be applied |  | Completed
| Destination Rule | Create the DestinationRule for staging-avenger-server service
Configure subset if there are more than one version of service
|  | Identify Circuit Breaking rules that needs to be applied |  |  | It can be implemented when incremental code changes are made in microservices
staging-avenger-mls
| Pod | Create pod for staging-avenger-mls | 1 | Completed
|  | Identify the number of replicas to run |  | Completed
|  | Specify the avenger-mls image to be used for container |  | Completed
|  | Specify the port mappings for container |  | Completed
|  | Identify the environment vairables to be used | 1 | Completed
|  | Identify if some variable can be moved as Secrets | 1 | Completed
|  | Configure the container for health checks | 1 | Completed
| Service | Create the service for staging-avenger-mls pod | 0.5 | Completed
staging-avenger-appointment
| Pod | Create pod for staging-avenger-appointment | 1 | Completed
|  | Identify the number of replicas to run |  | Completed
|  | Specify the avenger-appointment image to be used for container |  | Completed
|  | Specify the port mappings for container |  | Completed
|  | Identify the environment vairables to be used | 1 | Completed
|  | Identify if some variable can be moved as Secrets | 0.5 | Completed
|  | Configure the container for health checks | 0.5 | Completed
| Service | Create the service for staging-avenger-appointment pod | 0.5 | Completed
staging-xray
|  | Create Xray Daemon using the aws-xray-kubernetes https://github.com/aws-samples/aws-xray-kubernetes | 3 | Completed | Needs to be decided after the demo
Microservice Incremental Code Changes
avenger-server avenger-mls avenger-appointment | Code Changes | Disable the the consul service discovery and use Kubernetes service discovery | 3 | Completed | Consul is getting used for feature Togglz/Find an alternative
|  | Disable the Hystrix Circuit Breaking and use Istio Circuit Breaking |  |  | We can leave it for first deployment
|  | Define the fallback method if the service returns 500 error response code |  |  | How to find the service api with same labels in k8s from application
|  | Decide what do we want to use for tracing AWS X-Ray or Jaeger/Zipkin and made the changes accordingly | 3
|  | Identify the places where Ribbon is getting used and disable it. LoadBalancing needs to be handled by Istio | 3 | Completed
|  | Build the new image and push it ECR |  | Not Required
Microservices Testing
| API Testing | Identify different api calls for each service to make sure that individual services are working | 1 | Completed
|  | Verify that service to service call is working | 2 | Completed
|  | Verify that load balancing is working | 2 | Completed
|  | Verify the Circuit breaking is working for each services |  | Completed
|  | Verify the logs are sent to Cloud Watch | 2 | Completed | Configure the Lambda functions
|  | Identify if there are any other test usecases | 1 | Completed
|  | Bugs and Fixes | 16 | Completed
Migrate to new EKS Cluster
| Route 53 | Next route some traffic to the EKS cluster by setting Round Robin DNS or Weighted Routing Policy | 3 | Completed
|  | Later move all the traffic to the new EKS cluster |  | Completed
| Fixes | Fix all the issues | 11 | Completed
|  | Total Hours | 120
| Security Check | Install Kube-bench and securely by running the checks documented in the CIS Kubernetes Benchmark. https://github.com/aquasecurity/kube-bench |  | Completed

## Sheet2
Open Task/Issues | Status
Add kubernetes tags to the public subnet so that it is allowd to create ALB. Currently tags has been added manually | Completed. Not Required anymore.
convert null_resource.aws-alb-ingress-controller to helm_release resource | Completed
Disable the Hystrix Circuit Breaking and use Istio Circuit Breaking
Define the fallback method if the service returns 500 error response code
Configure and enable MTLS for the service mesh/RBAC
We are hitting maximum quota of policies which is 10. We need to refactor , how we define the policies for eks.
PodSecurityPolicies are not available in EKS 1.11 AWS has planned to include it in 1.13 release
Horizontal Pod Scaling
Limit Resources
How to do versioning/revision in pod?
Gitlab CI/CD | High Priority
How the circuit breaking works in case of external service is down and return 500 error
How would local development work. Avenger talking mls in kubernetes? | Completed
How to do Cross cutting concerns
istio-ingress.yaml:
- alb.ingress.kubernetes.io/certificate-arn -> we need to switch terraform data.acm_certificate
- alb.ingress.kubernetes.io/tags - "dev" would not work for prod - not sure if we need these tags
#NAME?
- need logs to s3 (compare with monolith): alb.ingress.kubernetes.io/load-balancer-attributes:access_logs.s3.enabled=true,access_logs.s3.bucket=avenger-lb-access-logs,access_logs.s3.prefix=istio-ingress-alb
- re: logs we need to check where monolith logs were used; I renamed path for the bucket
- manage R53 entry: https://kubernetes-sigs.github.io/aws-alb-ingress-controller/guide/external-dns/setup/
2. logging -
- fix logentries format,
- separate cloudwatch buckets (my commits/comments from 2 days ago)
3. permissions - in log entries I see AmazonErrorCode: AWS.SimpleQueueService.NonExistentQueue\n" - it could be caused by permission issue (either we need kube2im or code deployed to stage is old/broken)

## Sheet3
[INFO] 2 Worker Node Security Configuration
[INFO] 2.1 Kubelet
[FAIL] 2.1.1 Ensure that the --allow-privileged argument is set to false (Scored)
[PASS] 2.1.2 Ensure that the --anonymous-auth argument is set to false (Scored)
[PASS] 2.1.3 Ensure that the --authorization-mode argument is not set to AlwaysAllow (Scored)
[FAIL] 2.1.4 Ensure that the --client-ca-file argument is set as appropriate (Scored)
[PASS] 2.1.5 Ensure that the --read-only-port argument is set to 0 (Scored)
[PASS] 2.1.6 Ensure that the --streaming-connection-idle-timeout argument is not set to 0 (Scored)
[FAIL] 2.1.7 Ensure that the --protect-kernel-defaults argument is set to true (Scored)
[PASS] 2.1.8 Ensure that the --make-iptables-util-chains argument is set to true (Scored)
[PASS] 2.1.9 Ensure that the --hostname-override argument is not set (Scored)
[PASS] 2.1.10 Ensure that the --event-qps argument is set to 0 (Scored)
[FAIL] 2.1.11 Ensure that the --tls-cert-file and --tls-private-key-file arguments are set as appropriate (Scored)
[PASS] 2.1.12 Ensure that the --cadvisor-port argument is set to 0 (Scored)
[FAIL] 2.1.13 Ensure that the --rotate-certificates argument is not set to false (Scored)
[PASS] 2.1.14 Ensure that the RotateKubeletServerCertificate argument is set to true (Scored)
[PASS] 2.1.15 Ensure that the Kubelet only makes use of Strong Cryptographic Ciphers (Not Scored)
[INFO] 2.2 Configuration Files
[FAIL] 2.2.1 Ensure that the kubelet.conf file permissions are set to 644 or more restrictive (Scored)
[FAIL] 2.2.2 Ensure that the kubelet.conf file ownership is set to root:root (Scored)
[FAIL] 2.2.3 Ensure that the kubelet service file permissions are set to 644 or more restrictive (Scored)
[FAIL] 2.2.4 Ensure that the kubelet service file ownership is set to root:root (Scored)
[FAIL] 2.2.5 Ensure that the proxy kubeconfig file permissions are set to 644 or more restrictive (Scored)
[FAIL] 2.2.6 Ensure that the proxy kubeconfig file ownership is set to root:root (Scored)
[WARN] 2.2.7 Ensure that the certificate authorities file permissions are set to 644 or more restrictive (Scored)
[WARN] 2.2.8 Ensure that the client certificate authorities file ownership is set to root:root (Scored)
[FAIL] 2.2.9 Ensure that the kubelet configuration file ownership is set to root:root (Scored)
[FAIL] 2.2.10 Ensure that the kubelet configuration file has permissions set to 644 or more restrictive (Scored)